## Gantt Chart
WBS NUMBER | TASK TITLE | TASK OWNER | PCT OF TASK COMPLETE | TEAM FORMATION | [20 empty] | PLANNING | [13 empty] | RESEASE ONE | [20 empty] | RELEASE TWO | [27 empty] | RELEASE THREE
|  |  |  | WEEK 1 | [6 empty] | WEEK 2 | [6 empty] | WEEK 3 | [6 empty] | WEEK 4 | [6 empty] | WEEK 5 | [6 empty] | WEEK 6 | [6 empty] | WEEK 7 | [6 empty] | WEEK 8 | [6 empty] | WEEK 9 | [6 empty] | WEEK 10 | [6 empty] | WEEK 11 | [6 empty] | WEEK 12 | [6 empty] | WEEK 13
|  |  |  | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S | S | M | T | W | R | F | S
1 | 1-page "Release" Summary
1.1 | Informative Overview | Utkarsh | 100% | bar: WEEK 6 S to WEEK 6 T
1.2 | Features and progress | Aarnav, Aryan | 100% | bar: WEEK 6 M to WEEK 6 R; WEEK 8 S to WEEK 9 T
1.3 | Precise and Informative Summary of Project | Aryan | 100% | bar: WEEK 9 S to WEEK 10 S; WEEK 11 S to WEEK 12 S; WEEK 13 R to WEEK 13 F
2 | 4-page Project Plan
2.1 | Forming the group | Aarnav | 100% | bar: WEEK 1 S to WEEK 1 M
2.2 | Brain Storming | Everyone | 100% | bar: WEEK 1 F to WEEK 3 S
2.3 | Initial Plan | Everyone | 100% | bar: WEEK 2 F to WEEK 3 T
2.4 | Decide on Topic | Everyone | 100% | bar: WEEK 3 S to WEEK 3 T
2.5 | Scope | Everyone | 100% | bar: WEEK 3 T to WEEK 4 W
2.6 | Project Estimate Constrains | Aarnav | 100% | bar: WEEK 4 T to WEEK 5 M
2.7 | Project Plan | Utkarsh | 100% | bar: WEEK 5 T to WEEK 5 W; WEEK 6 S to WEEK 7 S; WEEK 8 S to WEEK 10 M; WEEK 11 S to WEEK 12 M
3 | 10-page Analysis and Design Report
3.1 | Design Report | Aarnav, Avi | 100% | bar: WEEK 12 M to WEEK 13 R
4 | Executable Code
4.1 | Software Req. Code Planning | Everyone | 100% | bar: WEEK 4 W to WEEK 5 M
4.2 | Version 1 coding | Everyone | 100% | bar: WEEK 5 W to WEEK 7 R
4.3 | Version 2 planning | Everyone | 100% | bar: WEEK 8 S to WEEK 8 S
4.4 | Version 2 coding | Utkarsh, Pratul, Kush | 100% | bar: WEEK 10 S to WEEK 10 F
4.5 | Version 3 planning | Everyone | 100% | bar: WEEK 11 R to WEEK 12 M
4.6 | Version 3 coding | Kush | 100% | bar: WEEK 12 T to WEEK 12 F
5 | Executable Test Code
5.1 | Version 1 test cases | Pratul, Kush, Aryan | 100% | bar: WEEK 7 W to WEEK 8 S
5.3 | Version 2 test cases | Pratul, Kush, Utkarsh | 100% | bar: WEEK 10 S to WEEK 11 W
5.3 | Version 3 test cases | Pratul, Kush | 100% | bar: WEEK 12 S to WEEK 13 M
6 | Bug Report
6.1 | Bug Reports | Pratul | 100% | bar: WEEK 9 S to WEEK 9 S; WEEK 11 W to WEEK 11 S; WEEK 13 T to WEEK 13 W
7 | 7-page self-assessment report
7.1 | Log the progress in weekly log | Everyone | 100% | bar: WEEK 1 M; WEEK 1 S; WEEK 2 F to WEEK 3 S; WEEK 3 T; WEEK 3 S; WEEK 4 W; WEEK 4 S; WEEK 5 M; WEEK 5 W; WEEK 5 S; WEEK 6 F to WEEK 6 S; WEEK 7 S; WEEK 8 S to WEEK 9 S; WEEK 9 R; WEEK 9 S; WEEK 10 M; WEEK 11 T; WEEK 11 S; WEEK 12 M; WEEK 12 W; WEEK 12 S to WEEK 13 W
7.2 | 1 page self reflection/ self evaluation | Everyone | 100% | bar: WEEK 13 T to WEEK 13 F